## Project Planner
Gaant Chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 3 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Risk Assesment | 1 | 1 | 1 | 1 | 100%
Rewrite Brief | 1 | 1 | 1 | 1 | 100%
Research CF to SIF method | 2 | 2 | 2 | 1 | 100%
Make Gaant Chart | 2 | 1 | 3 | 1 | 50%
Research alternate numerical methods | 2 | 2 | 3
Simulate Westergaard problem | 2 | 1 | 2 | 1 | 100%
Simulate problem on page 205 of cracks handbook | 2 | 2 | 2 |  | 50%
Draft Project Plan | 3 | 2
Submit Initial Project Report | 10 | 5
Submit Project Plan | 10 | 5
Submit project outline report | 15 | 6
Submit project pack | 21 | 8
Activity 21 | 14 | 8 | 14 | 2 | 44%
Activity 22 | 14 | 7 | 14 | 3 | 0%
Activity 23 | 15 | 4 | 15 | 8 | 12%
Activity 24 | 15 | 5 | 15 | 3 | 5%
Activity 25 | 15 | 8 | 15 | 5 | 0%
Activity 26 | 16 | 28 | 16 | 30 | 50%